## Use Case Template
Project Title: SecureLink VPN Release #: 2 (CST-452 Development Phase) Sprint #: Milestone 4 – 2nd Code Iteration
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate | Assigned To
US-01 | Authentication | As a(n) User | I would like to register for an account with an email and password | so that I can create a SecureLink account | 4 | Danny Abeuov
US-02 | Authentication | As a(n) System | I would like to hash and store the password with BCrypt rather than plaintext | so that credentials are protected if the database is ever exposed | 2 | Danny Abeuov
US-03 | Authentication | As a(n) System | I would like to reject a registration if the email is already in use | so that each account stays unique | 1 | Danny Abeuov
US-04 | Authentication | As a(n) User | I would like to log in with my email and password | so that I can access the VPN client | 3 | Danny Abeuov
US-05 | Authentication | As a(n) System | I would like to issue a signed JWT (with an expiration) on successful login/registration | so that the API can authenticate later requests without server-side session state | 3 | Danny Abeuov
US-06 | Session Management | As a(n) User | I would like to be blocked from starting a second session while one is already active | so that a single account can never run two tunnels at once (FR-3/FR-15) | 3 | Danny Abeuov
US-07 | Session Management | As a(n) User | I would like to choose a relay region (New York/US-East or Germany) before connecting | so that I control where my traffic exits to the internet | 3 | Danny Abeuov
US-08 | Session Management | As a(n) System | I would like to assign each session a unique tunnel IP inside the chosen relay's subnet | so that two clients on the same relay never collide | 3 | Danny Abeuov
US-09 | Session Management | As a(n) User | I would like to disconnect my session on demand | so that my WireGuard peer is removed from the relay and my session is marked ended | 2 | Danny Abeuov
US-10 | Session Management | As a(n) System | I would like to detect a session left "active" by a crashed previous run and close it automatically on next launch | so that a stale record can't lock the user out of Connect with a 409 | 4 | Danny Abeuov
US-11 | WireGuard Tunnel | As a(n) User | I would like to have the client generate my WireGuard key pair locally | so that my private key is never transmitted to the server | 3 | Danny Abeuov
US-12 | WireGuard Tunnel | As a(n) User | I would like to have the client bring up a WireGuard tunnel using the relay's connection details | so that my traffic is encrypted and routed through the chosen relay | 6 | Danny Abeuov
US-13 | WireGuard Tunnel | As a(n) User | I would like to have the tunnel torn down cleanly when I disconnect | so that no orphaned tunnel service keeps running in the background | 4 | Danny Abeuov
US-14 | WireGuard Tunnel | As a(n) User | I would like to have the app detect and clean up a leftover tunnel service from a crashed previous run | so that my internet access isn't silently broken with no obvious cause | 4 | Danny Abeuov
US-15 | WireGuard Tunnel | As a(n) User | I would like to see live session duration and upload/download totals while connected | so that I can monitor my active session | 3 | Danny Abeuov
US-16 | Kill Switch | As a(n) User | I would like to have a kill switch that blocks outbound traffic that isn't going through the tunnel | so that my real traffic never leaks if the tunnel drops unexpectedly | 6 | Danny Abeuov
US-17 | Kill Switch | As a(n) User | I would like to have the kill switch automatically disabled on disconnect (or on startup cleanup) | so that my normal internet access is restored afterward | 2 | Danny Abeuov
US-18 | Relay Orchestration | As a(n) System | I would like to have the backend call each relay's peer-management API to add/remove WireGuard peers | so that the client never needs direct SSH access to a relay | 6 | Danny Abeuov
US-19 | Relay Orchestration | As a(n) System | I would like to have a peer-removal failure on the relay side not block the user's local disconnect | so that a brief relay/network blip can never trap a user in a full-tunnel state | 3 | Danny Abeuov
US-20 | Admin | As a(n) Admin User | I would like to view all currently active sessions across every user | so that I can monitor system usage | 2 | Danny Abeuov
US-21 | Admin | As a(n) Admin User | I would like to forcibly revoke an active session | so that I can end an abusive or stuck session | 2 | Danny Abeuov
US-22 | Infrastructure | As a(n) System/DevOps | I would like to provision both relay droplets (US + Germany) via Terraform with WireGuard and the peer-management API installed by cloud-init | so that relay setup is repeatable instead of manual | 8 | Danny Abeuov
US-23 | Infrastructure | As a(n) System | I would like to have each relay's firewall explicitly allow forwarded tunnel traffic (ufw route allow) | so that clients can actually reach the internet through the relay, not just complete a handshake | 2 | Danny Abeuov
US-24 | Secure Credential Storage | As a(n) User | I would like to have my auth token stored in Windows Credential Manager instead of an in-memory field | so that my session token survives restarts securely | 3 | Danny Abeuov
US-25 | Tunnel Health Monitoring | As a(n) User | I would like to have the app actively detect a stale/dropped handshake and alert me | so that I know the tunnel is down instead of assuming I'm still protected | 4 | Danny Abeuov
| Percent of user stories complete for this iteration (Milestone 4): |  | 23 of 25 = 92% at Milestone 4; 25 of 25 = 100% after Milestone 6 (US-24 and US-25 completed)
| Percent of user stories complete for entire project (est., across M4–M6): |  | 100%